## Product Backlog
Project Name | saucedemo
Client | ExcelR
Created By | Anuj Manwatkar,Abusufiyan Akkalkotkar,Karthik,Harathe,Abhi Sathwika
Creation Date | 2024-10-22
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
Build_B01 | US_01 | Verify presence of the dropdown filter | Dropdown filter option at the right corner should be present Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the dropdown filter element is visible on the homepage.
Build_B02 | US_02 | Verify default selection in the dropdown | Dropdown option at the right corner with default filter(A-Z) should be present Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the dropdown filter with default selection should be (A-Z) filtering.
Build_B03 | US_03 | Verify sorting functionality using "Price (low to high)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify the dropdown filter sorting functionality using "Price (low to high)"
Build_B04 | US_04 | Verify sorting functionality using "Price (high to low)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify the dropdown filter sorting functionality using "Price (high to low)"
Build_B05 | US_05 | Verify sorting functionality using "Name (A to Z)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the products are sorted alphabetically from A to Z.
Build_B06 | US_06 | Verify sorting functionality using "Name (Z to A)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the products are sorted alphabetically from Z to A.
Build_B07 | US_07 | Verifying the Search bar on the homepage. | Search bar option should be visible on the top middle of the homepage to search the desired product. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the Search bar is present on the top middle of the homepage
Build_B08 | US_08 | Verify that the side menu bar opens upon clicking Hamburger Icon. | Hamburger Icon should be visible at the left top corner of the homepage. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the Hamburger icon is present on the top left corner of the homepage.
Build_B09 | US_09 | Verify that clicking "About" in the side menu bar navigates to the About page | In the side menu bar the "About" option should be present in the list of options. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3. Click on the side menu bar Hamburger Icon. 4.Select the "About" option and it should navigate to the About link page.
Build_B10 | US_10 | Verify that clicking the cross mark in the side menu bar closes the menu | In the side menu bar the cross mark should be present to click and close the side menu bar. Note: User is logged into the application and is on the homepage |  | 1.Log in to the application. 2.User will be in homepage. 3. Click on the side menu bar Hamburger Icon. 4.Select the cross mark option and it should close the side menu bar.
Epic-1

## Sprint Planning
Project Name | Saucedemo
Client | Excel R
Created By | Anuj Manwatkar,Sai Uday Kiran,Karthik,Harathe,Abhi Sathwika
Attendees | Anuj Manwatkar,Abusufiyan Akkalkotkar,Karthik,Harathe,Abhi Sathwika
Creation Date | 2024-10-22
Epic | User Story ID | Feature/Title | User Story | Sprint | Status | Acceptance Creteria
Epic-1 | US_01 | Verify presence of the dropdown filter | Dropdown option at the right corner with default filter(A-Z) should be present Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the dropdown filter element is visible on the homepage.
| US_02 | Verify default selection in the dropdown | Dropdown option at the right corner with default filter(A-Z) should be present Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the dropdown filter with default selection should be (A-Z) filtering.
| US_03 | Verify sorting functionality using "Price (low to high)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify the dropdown filter sorting functionality using "Price (low to high)"
| US_04 | Verify sorting functionality using "Price (high to low)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify the dropdown filter sorting functionality using "Price (high to low)"
| US_05 | Verify sorting functionality using "Name (A to Z)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the products are sorted alphabetically from A to Z.
| US_06 | Verify sorting functionality using "Name (Z to A)" | Dropdown option at the right corner with default filter(A-Z) should be present and should be clickable to apply the required filter options from the dropdown. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the products are sorted alphabetically from Z to A.
| US_07 | Verifying the Search bar on the homepage. | Search bar option should be visible on the top middle of the homepage to search the desired product. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the Search bar is present on the top middle of the homepage
| US_08 | Verify that the side menu bar opens upon clicking Hamburger Icon. | Hamburger Icon should be visible at the left top corner of the homepage. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3.Verify that the Hamburger icon is present on the top left corner of the homepage.
| US_09 | Verify that clicking "About" in the side menu bar navigates to the About page | In the side menu bar the "About" option should be present in the list of options. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3. Click on the side menu bar Hamburger Icon. 4.Select the "About" option and it should navigate to the About link page.
| US_10 | Verify that clicking the cross mark in the side menu bar closes the menu | In the side menu bar the cross mark should be present to click and close the side menu bar. Note: User is logged into the application and is on the homepage | 1 |  | 1.Log in to the application. 2.User will be in homepage. 3. Click on the side menu bar Hamburger Icon. 4.Select the cross mark option and it should close the side menu bar.

## Test scenarios
,
Project Name | Saucedemo
Module Name | Saucedemo_Test_cases
Requirement Number | REQ001
Test case Type | User Interface Testing, Functional Testing
Reference Doccument | NA
Pre-condition | Saucedemo URL should be accessible
Test Data | https://www.saucedemo.com/v1/index.html
Requirement : | Dropdown option at the right corner with default filter(A-Z) should be present Note: User is logged into the application and is on the homepage | Homepage dropdown verification
Test Senario number | Description | Test Scenario Type | TE Name
User Story 1- Gudala Sai Uday Kiran
TSF_01 | Verify that the dropdown filter is visible and present on the homepage. | User Interface Testing
TSF_02 | Check if the default option in the dropdown filter is as expected from ("A to Z)". | Functional Testing
TSF_03 | Verify that selecting "Price (low to high)" sorts the products from the lowest to highest price. | Functional Testing
TSF_04 | Verify that selecting "Price (high to low)" sorts the products from the highest to lowest price. | Functional Testing
TSF_05 | Verify that selecting "Name (A to Z)" sorts the products alphabetically in ascending order. | Functional Testing
TSF_06 | Verify that selecting "Name (Z to A)" sorts the products alphabetically in descending order. | Functional Testing
TS_07 | Verifying the visibility of Search bar icon on the homepage to search for the desired products. | User Interface Testing
TS_08 | Verify that the side menu bar opens when clicked on Hamburger Icon. | Functional Testing
TS_09 | Verify that clicking on "About" option in the side menu bar navigates to the About page | Functional Testing
TS_10 | Verify that clicking the cross mark in the side menu bar closes the side menu | Functional Testing
User Story 2- Shahid
User Story 3-Shiva
User Story 4-Keerthi
User Story 5-Gayathri Priya

## Test cases
Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date | DEFECT NO
TSF_01_TC01 | Dropdown visibility | Verify that the dropdown filter is visible and present on the homepage. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. To check if the dropdown filter is present in the homepage. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The dropdown filter should be visible and clickable. | The dropdown filter is visible and clickable. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_02_TC02 | Default Dropdown filter verification | Check if the default option in the dropdown filter is as expected from "(A to Z)". | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. To check if the dropdown filter with default (A-Z) is applied for items sorting. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The default filter selection should be "Name (A to Z)" | The default filter selection is "Name (A to Z)". |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_03_TC03 | Dropdown filter sorting from (Low-High) price. | Verify that selecting "Price (low to high)" sorts the products from the lowest to highest price. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Click on the dropdown filter. Select the option "Price (low to high)". Verify that the products are sorted in ascending order of price. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The products should be sorted from the lowest to the highest price. | The products are sorted from the lowest to the highest price. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_04_TC04 | Dropdown filter sorting from (High-Low) price. | Verify that selecting "Price (high to low)" sorts the products from the highest to lowest price. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Click on the dropdown filter. Select the option "Price (high-low)". Verify that the products are sorted in descending order of price. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The products should be sorted from the highest to the lowest price. | The products are sorted from the highest to the lowest price. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_05_TC05 | Dropdown filter sorting from (A-Z) alphabetically. | Verify that selecting "Name (A to Z)" sorts the products alphabetically in ascending order. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Click on the dropdown filter. Select the option "Name (A to Z)". Verify that the products are sorted alphabetically from A to Z. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The products should be sorted alphabetically from A to Z. | The products aree sorted alphabetically from A to Z. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_06_TC06 | Dropdown filter sorting from (Z-A) alphabetically. | Verify that selecting "Name (Z to A)" sorts the products alphabetically in descending order. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Click on the dropdown filter. Select the option "Name (Z to A)". Verify that the products are sorted alphabetically from Z to A. | Login Credentials (for accessing the dropdown filter on homepage) Username: standard_user Password: secret_sauce | The products should be sorted alphabetically from Z to A. | The products are sorted alphabetically from Z to A. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_07_TC07 | Search bar icon visibility | Verifying the visibility of Search bar icon on the homepage to search for the desired products. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. To check if the Search bar icon is present in the homepage. | Login Credentials (for accessing the Search bar on homepage) Username: standard_user Password: secret_sauce | The search bar should be visible on the homepage as per the expected design and functionality. | The search bar is not visible on the homepage as per the actual design and functionality. |  |  | Abusufiyan | fail | 2024-10-22 | 2024-10-22 | TSF_07_TC07_Defect_01
TSF_08_TC08 | Side menu bar functioning when clicked on icon. | Verify that the side menu bar opens when clicked on Hamburger Icon. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Locate the side menu button hamburger icon. Click on the side menu button. Observe whether the side menu bar opens as expected. | Login Credentials (for accessing the main menu bar on homepage) Username: standard_user Password: secret_sauce | The side menu bar should smoothly slide open, making its contents visible. | The side menu bar is smoothly opened, making its contents visible. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_09_TC09 | Clicking on "About" option on side menu bar. | Verify that clicking "About" in the side menu bar navigates to the correct "About" page of the website. | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Locate the side menu button hamburger icon. Click on the side menu button. Click on the "About" option from the list of options in the menu. | Login Credentials (for accessing the main menu on homepage) Username: standard_user Password: secret_sauce | After clicking "About" the system should successfully navigate to the "About" page. | After clicking "About" the system have successfully navigated to the "About" page. |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22
TSF_10_TC10 | Clicking on "Cross mark" option on side menu bar. | Verify that clicking the cross mark in the side menu bar closes the side menu | Launch the Browser | Chrome Browser should be installed in your system and internet should be available | yes chrome browser launched | yes chrome browser launched | critical | p1 | Abusufiyan | pass | 2024-10-22 | 2024-10-22
|  |  | Login with valid credentials. Locate the side menu button hamburger icon. Click on the side menu button. Locate the cross mark (X) button within the side menu bar. Click the cross mark to close the side menu. Observe the system's behavior and verify if the side menu closes. | Login Credentials (for accessing the main menu on homepage) Username: standard_user Password: secret_sauce | Clicking the cross mark should immediately close the side menu. | The side menu does not close after clicking the cross mark.- |  |  | Abusufiyan | pass | 2024-10-22 | 2024-10-22 | TSF_10_TC10_Defect_02

## Defects
Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
TSF_07_TC07_Defect_01 | Saucedemo | Search bar icon visibility check | REQ001 | TSF_07_TC07 | Search bar icon visibility check on the homepage | To check that when user is on the homepage the the search bar icon should be visible | Search bar icon is not displayed | High | p1 | Abusufiyan
TSF_10_TC10_Defect_02 | Saucedemo | Cross mark functionality check in side menu bar. | REQ002 | TSF_10_TC10 | Cross mark functionality check in side menu bar | To check the functinality of Cross mark in the side menu bar. | Side menu bar not closed when clicked on Cross mark. | High | p1 | Abusufiyan

## Defect_Snapshots
Defect ID | Test Case ID | Failed Screenshots
TSF_07_TC07_Defect_01 | TSF_07_TC07
TSF_10_TC10_Defect_02 | TSF_10_TC10

## Story_Point_Effort_and_Reason
User Story1-Sai Uday Kiran
Project Name :- | Saucedemo
Story Point :- | 2
Reason for story point :- | User is able to apply different filter options from the dropdown. User should see the Search bar on Homepage. User should able to access side menu bar and also close the side menu bar.
Efforts(in hours) :- | 12
Reason for Efforts :- | Test cases Preparation:10 Test case excecution:10 Raising Bugs:2
User Story2-Shahid
User Story3-Shiva
User Story4-Keerthi
User Story5-Gayathri priya

## Test report
SNO | TE NAME | TOTAL TEST CASE | PASS | FAIL | BLOCKERS | NOT EXECUTED | PASS RATIO (%) formula use : D2/C2*100 | TEST IN PROGRESS | TOTAL DEFECT
1 | Abusufiyan Akkalkotakar | 10 | 8 | 2 | 0 | 0 | 80 | 2 | 2
TOTAL |  | 45 | 23 | 22 | 0 | 0 |  | 0